## Master Calendar
Middle States Spring 2023 Visit - Master Schedule
Event | Timeline | Year | Status | Actions Needed | Area Responsible | Notes
Self-Study Institute | Sept-Nov | 2020 | Complete | Complete training webinars | Middle States | Area VPs were asked for nominations for representatives from their divisions to participate in this training: Michelle Currier (Academic Affairs), Amanda Crump (Administration), Kristen Roberts (Student Affairs), Beth Gravlin (Advancement), Kirk Jones (Academic Assessment & SS Co-Chair), Peggy De Cooke (Provost), and Johanna Lee (Non-Academic Assessment & SS Co-Chair).
Ranking of the existing institutional priorities | Dec-Jan | 2020-21 | Complete | Create a survey and distribute it to the campus community. Survey asks individuals to rank the existing institutional priorities in terms of top 3 priorities. | SS Co-Chairs & IR | The Director of Assessment developed and distributed the survey with IR. The NAAC chair encouraged the NAA areas to participate. An open forum was held to discuss the results as a sort of "kick off" to the start of our 22-23 self-study. The survey results are in a tab below.
Standards Committee composition determined | Jan | 2021 | Complete | Send letters to the chairs and members. | Provost's Office & VPG | A proposed list of committee members and chairs was reviewed at VPG for approval.
Evidence inventory & repository construction | Dec-Mar | 20-21 | Complete | Create Team and link to SharePoint. | SS Co-Chairs | A Team was created with designated channels for each of the standards working groups. The Team has a link to SharePoint where documents collected in Phase 1 of evidence collection can be stored and accessible to the evidence inventory team and Steering Committee. Members will be added prior to the first meeting. Repository: 1. Initial area where working groups put their info. (Teams) a. This is reviewed by Steering Committee and evidence inventory team and move to: 2. A secondary repository that is organized in an intuitive manner in case the review team wants to do a deeper dive on anything. (URL) 3. Final documents used for evidence will be uploaded in the MS portal
Video conference with MSCHE VP Liaison & SS Co-Chairs | Jan-Feb | 2021 | Complete | Schedule a call with VP liason to discuss any questions and provide this timeline for completing tasks | Provost & SS Co-Chairs | The conference was scheduled and completed. Timelines and activities were discussed and approved.
Final selection of top 3 institutional priorities | Mar | 2021 | Complete | Review the survey results of the ranking of existing instituional priorities and make a final selection. | President | The top 3 priorities identified in the campus survey will be used: 1. Promote Academic Excellence, 2. Optimize Enrollement, 3. Improve Operational Effectiveness. Additionally, as a result of the discussion in the campus forum, Enhance Diversity & Welcome will be woven throughout the self-study as a consistent theme in all of the work we do.
Creation of a communication plan | Mar | 2021 | Complete | Create a communication plan with benchmarks for completing tasks and communication results to appropriate consitituencies. | SS Co-Chairs | Do Phase 2 in phases: 1. Provide working groups with a date to submit evidence for review. Staggering these dates will give us time to review and give them feedback. They can then go back and fill in gaps.
Initial Steering Committee meeting | Feb | 2021 | Complete |  | SS Co-Chairs | Reviewed the Standards Working Group Charge, the review process, the communication plan, and the 7 standards. Provided resources and first steps.
Self-Study Design document | July | 2021 | Complete | The design document was submitted to MSCHE VP liason for review. | Provost & SS Co-Chairs | The document was worked on and reviewed by: SS Co-Chairs, Provost, and the President. It was reviewed, commented on, and approved by MSCHE VP liason.
Self-Study preparation visit by MSCHE VP liaison | Early fall | 2021 | Complete | Fall visit took place on 10/7/21. The following meetings were held with the MSCHE VP laison: VPs, Steering Committee, Open Campus Forum, SS Co-Chairs. | SS Co-Chairs | The self-study document was approved.
Complete evidence inventory & data repository | Early summer | 2021 | Complete | Steering Committee members were provided with access to Teams and multiple tools for repository. | SS Co-Chairs | The initial respository will be in Teams.
Standards Working Group reports submitted | November | 2021 | Pending | Working group chairs will submit a date for completion of review to the SS Co-Chairs. | Steering Committee | Standard I: 10/15/21 Standard II: 10/25/21 Standard III: 10/18/21 Standard IV: 10/15/21 Standard V: 10/25/21 Standard VI: 10/25/21 Standard VII: Complete
Review of Standards Working Group reports | November-December | 2021 |  |  | SS Co-Chairs
Reports returned to the Standard Working groups with revision suggestions | December-March | 2021 |  |  | SS Co-Chairs
Standards Working Groups revise material and resubmit | January | 2022 |  |  | Steering Committee
Middle States Team Chair selection begins | January | 2022 |  |  | Middle States
First draft of Self-Study complete | March | 2022 |  |  | SS Co-Chairs
Middle States Team Chair preliminary visit | Fall | 2022 |  |  | Middle States
Submit Self-Study and evidence | 6 weeks prior to on-site evaluation | 2022-12-01 |  |  | SS Co-Chairs
On-site evaluation visit | Spring | 2023 |  |  | Middle States
Commission action | June or Nov | 2023 |  |  | Middle States

## Institutional Rankings Survey
| Ranked 1st |  | Ranked 2nd |  | Ranked 3rd |  | Ranked 4th |  | Ranked 5th |  | Ranked 6th |  | Ranked 7th |  | Total
| % | N | % | N | % | N | % | N | % | N | % | N | % | N | N
Promote Academic Excellence | 54.76% | 46 | 10.71% | 9 | 14.29% | 12 | 7.14% | 6 | 8.33% | 7 | 3.57% | 3 | 1.19% | 1 | 84
Improve Operational Effectiveness | 9.52% | 8 | 21.43% | 18 | 17.86% | 15 | 10.71% | 9 | 14.29% | 12 | 19.05% | 16 | 7.14% | 6 | 84
Optimize Enrollment | 15.48% | 13 | 23.81% | 20 | 17.86% | 15 | 20.24% | 17 | 8.33% | 7 | 11.9% | 10 | 2.38% | 2 | 84
Focus on Sustainability | 2.38% | 2 | 5.95% | 5 | 10.71% | 9 | 8.33% | 7 | 21.43% | 18 | 22.62% | 19 | 28.57% | 24 | 84
Enhance Diversity & Welcome | 7.14% | 6 | 10.71% | 9 | 17.86% | 15 | 23.81% | 20 | 17.86% | 15 | 8.33% | 7 | 14.29% | 12 | 84
Create a Robust, Active, and Enriching Campus Life | 3.57% | 3 | 14.29% | 12 | 16.67% | 14 | 16.67% | 14 | 19.05% | 16 | 19.05% | 16 | 10.71% | 9 | 84
Build Greater Awareness of SUNY Canton | 7.14% | 6 | 13.1% | 11 | 4.76% | 4 | 13.1% | 11 | 10.71% | 9 | 15.48% | 13 | 35.71% | 30 | 84
Promote Academic Excellence | Rank 1
Improve Operational Effectiveness | Rank 3
Optimize Enrollment | Rank 2
Focus on Sustainability | Rank 7
Enhance Diversity & Welcome | Rank 4
Create a Robust, Active, and Enriching Campus Life | Rank 5
Build Greater Awareness of SUNY Canton | Rank 6